## Product Backlog
ID | Sprint | User Story / Task | Priority | Assigned To | Start Date | Target Date | Status | Notes
S1-1 | Sprint 1 | User Authentication (Login/Register) | High | Omkar Podey | Feb 22 | Mar 5 | Done | JWT + bcrypt, login/register endpoints & UI
S1-2 | Sprint 1 | Database Schema & API Validation | High | Omkar Podey | Feb 22 | Mar 1 | Done | 7 SQLAlchemy models, Pydantic schemas
S1-3 | Sprint 1 | Invite Code System | High | Omkar Podey | Feb 28 | Mar 10 | Done | Code generation, expiry, usage limits, join flow
S1-4 | Sprint 1 | Channel Management | High | Omkar Podey | Mar 3 | Mar 14 | Done | Channel CRUD, membership, target units
S1-5 | Sprint 1 | Server Creation | High | Anmol Rastogi | Feb 22 | Mar 5 | Done | Server CRUD with owner/member roles
S1-6 | Sprint 1 | Unified Chat Feed | High | Anmol Rastogi | Feb 28 | Mar 10 | Done | Message feed with pagination & grouping
S1-7 | Sprint 1 | WebSocket Real-Time Messaging | High | Anmol Rastogi | Mar 3 | Mar 14 | Done | ConnectionManager, broadcast, live status
S1-8 | Sprint 1 | Polling Fallback Implementation | Medium | Anmol Rastogi | Mar 7 | Mar 15 | Done | 10-second polling when WebSocket unavailable
S2-1 | Sprint 2 | Structured Check-In System | High | TBD |  |  | Pending | Check-ins as data points tied to channel targets
S2-2 | Sprint 2 | Target Unit Configuration per Channel | High | TBD |  |  | Pending | Miles, pages, boolean completion per channel
S2-3 | Sprint 2 | Check-In Card UI (Distinct from Chat) | High | TBD |  |  | Pending | Visual distinction between chat and check-in cards
S2-4 | Sprint 2 | Daily Progress Dashboard | High | TBD |  |  | Pending | Dashboard showing member check-in status
S2-5 | Sprint 2 | Server-Side Timestamp Validation | Medium | TBD |  |  | Pending | Prevent streak manipulation
S2-6 | Sprint 2 | Authorization Enforcement (API-level) | Medium | TBD |  |  | Pending | Strict access control on all endpoints
S2-7 | Sprint 2 | Performance Goal (<500ms latency) | Medium | TBD |  |  | Pending | Validate message delivery under 500ms
S3-1 | Sprint 3 | Monthly Heatmap Visualization | Medium | TBD |  |  | Pending | GitHub-style contribution heatmap
S3-2 | Sprint 3 | Yearly Progress View | Medium | TBD |  |  | Pending | Long-term progress tracking
S3-3 | Sprint 3 | Streak Counter | Medium | TBD |  |  | Pending | Consecutive check-in tracking
S3-4 | Sprint 3 | Leaderboards (Monthly Ranking) | Low | TBD |  |  | Pending | Monthly rankings per channel
S3-5 | Sprint 3 | Emoji Reactions on Check-ins | Low | TBD |  |  | Pending | Social engagement feature
S3-6 | Sprint 3 | Coach Bot (Daily Summary + Nudges) | Medium | TBD |  |  | Pending | Rule-based bot: welcome, summaries, 48hr nudges
S3-7 | Sprint 3 | UI Polish & Usability Improvements | Low | TBD |  |  | Pending | One-tap check-ins, final UX pass

## Sprint 1 Summary
Metric | Value
Sprint | Sprint 1
Duration | February 22 - March 15, 2026
Total Tasks | 8
Completed | 8
Incomplete | 0
Completion Rate | 100%
Omkar's Tasks | 4
Anmol's Tasks | 4
Trello Board | https://trello.com/b/ufZ3LwJi/checkpoint-cs161
GitHub Repo | https://github.com/Omkar399/checkpoint